## Chart_01
2023-01-09
| Project Start Date: | 2023-01-08 | [5 empty] | 2023-01-09 |  |  |  | 2023-02-06 |  |  |  | 2023-03-06 |  |  |  | 2023-04-03
| Project Name: | Decentralized Voting System using Blockchain |  |  |  |  | Week Starting: | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24
# | Activity | Assigned To | Start | End | Days | Status | % Done
1 | Project kick-off | Assignee name | 2023-01-08 | 2023-01-30 | 16 | Completed | 100% | 2023-01-09: 0; 2023-01-30: u
2 | Project Task | Yash | 2023-01-10 | 2023-01-12 | 3 | Completed | 100% | bar: 2023-01-09
3 | Task 1 | Rishabh | 2023-01-13 | 2023-01-19 | 5 | Completed | 100% | bar: 2023-01-16
4 | Task 2 | Goutam | 2023-01-20 | 2023-01-23 | 2 | Completed | 100% | bar: 2023-01-23
5 | Task 3 | Yash | 2023-01-24 | 2023-01-29 | 4 | Completed | 100% | bar: 2023-01-23
6 | Task 4 | Rishabh | 2023-01-31 | 2023-02-02 | 3 | Completed | 100% | bar: 2023-01-30
7 | Task 5 | Goutam | 2023-02-04 | 2023-02-06 | 1 | Completed | 100% | bar: 2023-02-06
8 | Task 6 | Yash | 2023-02-08 | 2023-02-12 | 3 | Completed | 100% | bar: 2023-02-06
9 | Task 7 | Rishabh | 2023-02-14 | 2023-02-19 | 4 | Completed | 100% | bar: 2023-02-13
10 | Task 8 | Goutam | 2023-02-21 | 2023-02-26 | 4 | Completed | 100% | bar: 2023-02-20
11 | Task 9 | Yash | 2023-02-28 | 2023-03-05 | 4 | Completed | 100% | bar: 2023-02-27
12 | Task 10 | Rishabh | 2023-03-07 | 2023-03-12 | 4 | Completed | 100% | bar: 2023-03-06
13 | Task 11 | Goutam | 2023-03-14 | 2023-03-19 | 4 | Completed | 100% | bar: 2023-03-13
14 | Task 12 | Yash | 2023-03-21 | 2023-03-26 | 4 | Completed | 100% | bar: 2023-03-20
15 | Task 13 | Rishabh | 2023-03-28 | 2023-04-02 | 4 | Completed | 100% | bar: 2023-03-27
16 | Task 14 | Goutam | 2023-04-04 | 2023-04-09 | 4 | Completed | 100% | bar: 2023-04-03
17 | Task 15 | Goutam | 2023-04-11 | 2023-04-16 | 4 | Completed | 100% | bar: 2023-04-10
18 | Task 16 | Yash | 2023-04-18 | 2023-04-23 | 4 | Completed | 100% | bar: 2023-04-17
19 | Task 17 | Rishabh | 2023-04-25 | 2023-04-29 | 4 | Completed | 100% | bar: 2023-04-24
STATUSES
Not Started
In Progress
Pending
Completed
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))
Start = [Start, row above]+2
End = [End, row above]+7

## Literature_Review
S.No | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Paper Title | An E-Voting Protocol Based on Blockchain. | E-Matdaan: A Blockchain based Decentralized E-Voting System | De-Centralized E-voting system based on Smart Contract by using Blockchain Technology. | De-Centralized Voting System using Blockchain | History of Electoral Violence in Bihar. Research J. Humanities and Social Sciences | A Secure Electronic Voting System Using Blockchain Technology
Authors | Liu, Y.; Wang, Q. | S. Tandon, N. Singh, S. Porwal, Satiram and A. K. Maurya | A. M. Al-madani, A. T. Gaikwad, V. Mahale and Z. A. T. Ahmed, | A. Jangada, N. Dadlani, S. Raina, V. Sooraj and A. R. Buchade | Sanjay Kumar | K. Dhinakaran, P. M. Britto Hrudaya Raj, and D. Vinod
Year | 2017 | 2022 | 2020 | 2022 | 2015 | 2021
Methods (What work is done?) | Using Blind Signature: Used for signing encrypted messages, |  | 1. Overcomes centralized blockchain |  |  | 1. Developed a Secure EV System mitigating all threats. 2. Voter_ID is used as Identification. 3. Psuedocode is present for algorithm.
Validation (What methods they have used ? ) |  |  | 1. Used Solana as their transaction blokchain 2. Using Metamask for their Ethereum wallet. 3. Also, used Gnache |  |  | They proposed a blockchain structure in which a Node consists of: 1. Voter_ID{4 bytes} 2. Timestamp{4 bytes} 3. Signature{32 bytes} 4. Hash of previous block data{20 bytes} 5. Data Structure used: Merkel Tree {20 bytes}
Limitations (What things are left ?) |  |  | 1. Scalability issues due to absence of distributed databases. 2. Only used Aadhar Id as entry point in their application.

## Literature_review_updated
S.No | Authors | Paper Title | Journal | Conclusion | Methodology Used
1 | K. Dhinakaran, P. M. Britto Hrudaya Raj, and D. Vinod | A Secure Electronic Voting System Using Blockchain Technology | Information Management and Machine Intelligence. Lecture Notes in Networks and Systems, vol 166. Springer. (2023) doi: 10.1007/978-981-15-9689-6_34 | In this paper, we concluded that 1. Electoral Voting System is the best way to cast your vote by saving huge resources; 2. We can ensure that the voting process is more secure. 3. For reliability & zero fault tolerance of the system, as the Nodes grew, the time for the system was also raised in simulation to make it work. 4. Recording the voting result using hash values makes the system more secure. | They proposed a blockchain structure in which a Node consists of: 1. Voter_ID{4 bytes} 2. Timestamp{4 bytes} 3. Signature{32 bytes} 4. Hash of previous block data{20 bytes} 5. Data Structure used: Merkel Tree {20 bytes} 6. With respect to System Design the system continued sequence even if {(initial_node) lower (next_node)}: counter time++ 7. Then dimensions needed for the Recording Process ∝ Number Nodes.
2 | A. M. Al-madani, A. T. Gaikwad, V. Mahale and Z. A. T. Ahmed, | De-Centralized E-voting system based on Smart Contract by using Blockchain Technology. | International Conference on Smart Innovations in Design, Environment, Management, Planning and Computing. (2022) doi: 10.1109/ICSIDEMPC49020.2020.9299581. | In this paper, 1. Developed a Voting Application in a Decentralized Method with a Smart Contract based on Ethereum Blockchain technology as a network & decentralized database all in one for storage voter accounts, votes and candidate details. 2. Voter's Point of View: 1 VOTE == 1 PERSON == 0% DUPLICACY 3. Problems with Centralized Voting System (CVS) a. To overcome limitations b. Security Issues using Blockchain technology. | They proposed 4-Tier Architecture Design:- Level 1 : Authentication Web Page 1. Created an webpage which contains Authentication{using Aadhar Card} Level 2 : Authentication with DB 2. Used Mongo_DB as Governement Identity Verification Sevice. Level 3: Smart Contract Creation 3. Created Smart Contract includes {District, List Candidates} Level 4 : POA Network Deployment 4. Deploy a POA Network. It has 3 sub-modules:- a. Government {BootNode, Node1, Node2} b. Origo {BootNode, Node1, Node2} c. HR {BootNode, Node1, Node2}
3 | F. Þ. Hjálmarsson, G. K. Hreiðarsson, M. Hamdaqa and G. Hjálmtýsson, | Blockchain-Based E-Voting System | IEEE 11th International Conference on Cloud Computing. (2022) pp. 983-986, doi: 10.1109/CLOUD.2018.00151. | In this paper, 1. We analyzed the Traditional Voting System. 2. Benefits of Implementing a blockchain-based E-Voting system using various blockchain-based tools 3. Found using a Case study of the Manual Voting Process. 4. Also studied about comparison between the traditional voting system in use and the electronic voting system based on the blockchain. | They created 3-Tier Architecture Design:- A. Level 1 a. End User(HOME PAGE) b. Cast a Vote B. Level 2 a. Candidate Management b. Voter Management c. Result d. View Ledgers C. Level 3 a. Logout

## EVMs
Characterstics | EVM Details
Launched | 1982, Kerala
Cost Per Unit | 17000
Max. No of Votes(in M3 EVMs) | 2000 votes
Max. No. of Candidates(in M3 EVMs) | 384
Min. No of EVMs used in 2019 Elections | 3960000
Min. Expenditure used in 2019 Elections(in INR) | 67320000000
Avg. No of Elections in 1 year in India